## Sheet1
Task name | Duration | Start | Finish | Task Dependencies | Work
Project discussion | 1 day | 2023-10-17 | 2023-10-17 | None | Group
Project Plan/ Timeline | 1 day | 2023-10-18 | 2023-10-18 | Project discussion | Group
Written project phases | 3 days | 2023-10-19 | 2023-10-21 | Project Plan/ Timeline | Group
Business Analysis | 9 days | 2023-10-22 | 2023-10-30 | Written project phases | Individual
Solution Description | 8 days | 2023-10-31 | 2023-11-07 | Business Analysis | Individual
Project Budget | 13 days | 2023-11-08 | 2023-11-20 | Solution Description | Individual
Project Execution | 30 days | 2023-11-21 | 2023-12-20 | Project Budget | Group
Project Reflection | 5 days | 2023-12-21 | 2023-12-25 | Project Execution | Individual
Review and edit | 5 days | 2023-12-26 | 2023-12-30 | Project Reflection | Group
Project submission | 5 days | 2023-12-31 | 2024-01-04 | Review and edit | Group